# Custom-Branded Venue Vending RFP Template

Six-category execution methods, design approval cadence, refresh cycle planning, and operator scoring matrix

Use this RFP template to solicit branded-vending bids from operators that can deliver venue-grade visual treatment across full wraps, partial graphics, illuminated faces, digital displays, sponsor co-branding, and seasonal refreshes. Each section maps to a measurable specification your operator can attest to and that procurement can score.

# 1. Project overview

Venue type: (stadium / arena / theater / convention center / amphitheater — specify capacity and event mix)

Machine count + locations: (specify count by zone: main concourse, club level, VIP, BOH, exterior). Capability framing only — describe footprint requirements rather than naming anchor sites.

Contract term: Initial term (typically 3-5 years) with annual brand-refresh milestone reviews.

Branding scope: Full wrap, partial graphics, illuminated face, digital sidekick display, sponsor co-brand, seasonal refresh — operator to scope each category in their response.

# 2. Six-category execution methods (operator scope)

Operators must demonstrate capability across all six categories or clearly state which they subcontract. Reference NEMA 250 enclosure ratings and UL 751 (vending machines) compliance for any modified equipment.

| Category | Specification | Approval lead time | Refresh cadence |
| --- | --- | --- | --- |
| 1. Full-wrap vinyl | 3M IJ180mC / Avery MPI 1105 cast vinyl, 7-year outdoor durability, laminated overlay | 10-14 business days from final art | Annual refresh or per sponsor cycle |
| 2. Partial graphics + decals | Mid-grade 5-year vinyl on machine face and side panels; back panels left OEM | 5-7 business days | Semi-annual |
| 3. Illuminated front face | LED-backlit translucent vinyl with diffuser; ENERGY STAR compliant lighting | 3-4 weeks (custom fabrication) | Per sponsor cycle (typically 12-24 months) |
| 4. Digital sidekick display | 21"-32" commercial-grade display, CMS-driven; UL 60950 listed | 4-6 weeks (hardware lead) | Content refresh continuous; hardware 5-year |
| 5. Sponsor co-brand | Tiered logo placement matrix (primary / secondary / tertiary) with art-board guidelines | 2-3 weeks after sponsor contract | Per sponsor activation |
| 6. Seasonal/event refresh | Removable static-cling or quick-cure adhesive overlays for 30-90 day campaigns | 5-10 business days | 3-6 cycles per year |

# 3. Design approval cadence

1. Concept boards (T-30 days)

Operator submits 2-3 concept directions; venue marketing reviews against brand standards manual and any sponsor obligations. Reference internal style guide version number on every submission.

2. Production proof (T-14 days)

Full-scale color-accurate proof on actual substrate (vinyl, backlit material). Venue signs off on color (Pantone match within Delta-E ≤ 3), placement, and legibility.

3. Pre-install QA (T-3 days)

Operator confirms install crew, removal of prior wrap, surface prep per 3M Recommended Application Procedures, and site logistics with venue ops.

4. Install + sign-off (T-0)

Install supervised by venue marketing rep or designee. Photo documentation of all four sides; sign-off sheet retained for the duration of contract plus 3 years.

# 4. Refresh cycle planning

Build the refresh calendar against the venue's event mix, sponsor obligations, and seasonal moments. Operator commits to the refresh count in their bid; under-delivery triggers SLA credit per Section 7.

Tier-A wraps (full): 1-2 refreshes per year; typically aligned to season opener and post-season.

Tier-B partial graphics: 2-3 refreshes per year; aligned to sponsor activation windows.

Tier-C seasonal overlays: 3-6 refreshes per year; holiday, playoff, residency, and special-event tie-ins.

Digital content: Continuous (CMS push); operator provides scheduling tool access to venue marketing.

# 5. Operator capability matrix (scoring)

Procurement scores each operator on the following criteria; total weighted score determines award. Adjust weights to your venue's priorities.

| Criterion | Weight | Evidence required |
| --- | --- | --- |
| In-house design capability | 15% | Portfolio of 5+ comparable venue installs; capability framing acceptable — operator demonstrates skill set without naming specific anchor sites |
| Vinyl / wrap install crew | 15% | 3M Preferred Installer credential or equivalent; W-2 vs subcontract disclosed |
| Digital signage management | 10% | CMS platform demo (Stratacache, BrightSign, Enplug, or equivalent) |
| Refresh turnaround SLA | 15% | Operator commits to lead time per category in writing; 10% SLA credit clause |
| Sponsor integration experience | 10% | Sample tiered-logo matrix and 2 redacted sponsor agreements |
| Pricing transparency | 20% | Line-item breakdown: design / production / install / removal / refresh |
| Reporting + analytics | 10% | Sample monthly report: install photo log, refresh log, dwell-time analytics for digital sidekicks |
| Insurance + bonding | 5% | $2M GL minimum, $1M auto, $1M workers comp; bondable on contracts ≥ $250K |

# 6. Required attachments (operator response)

☐  Portfolio: 5+ comparable venue installs (capability framing acceptable; do not require operator to claim work at named anchor venues).

☐  Sample art-board guidelines and brand-compliance checklist.

☐  Sample monthly install + refresh report.

☐  Pricing schedule per Section 5, Criterion 6.

☐  Insurance certificate naming venue as additional insured.

☐  References: 3 venue marketing or procurement contacts (last 24 months).

# 7. SLA + credits

On-time install SLA: 100% of installs delivered on agreed install date. Each day late = 2% credit against that install line item.

Color-match SLA: Delta-E ≤ 3 against Pantone reference. Re-print at operator cost if exceeded.

Refresh-cadence SLA: Operator delivers committed refresh count per Section 4. Missed refresh = full credit for that cycle.

Damage repair SLA: Vandalism / damage repair within 7 business days of report (10 days for full-wrap). Photo-documented.

# 8. Submission instructions

Format: PDF response, electronic submission via procurement portal.

Due date: (specify — typically 30 days from RFP issue)

Q&A window: 10 business days after RFP issue; all questions answered in writing and distributed to all bidders.

Award notification: (specify — typically 45-60 days after submission close)

This template is informational; it is not legal advice. Have your venue's procurement counsel review before issue. Capability framing throughout — operators describe what they are equipped to deliver rather than claiming work performed at named anchor sites.