# 12-Phase Micro-Market Installation Checklist

Site survey, electrical, data, cold-chain, PCI-DSS, HR badge, and soft launch

Use this checklist to install a 50-200 employee corporate micro-market with zero post-launch surprises. Each phase maps to a contractually attestable deliverable; standards cited reference NEC 2023, FDA Food Code 2022, PCI-DSS v4.0, and ADA 2010 Standards Section 305-309.

# Phase 1 — Site survey (T-60 days)

☐  Measured kiosk footprint (typically 24 inch × 24 inch base + 18 inch clearance behind for cabling).

☐  Measured fixture floor plan (coolers 30 inch × 72 inch, ambient racks per planogram).

☐  ADA 305 clear floor space 30 inch × 48 inch verified at every operable part (kiosk + each cooler door).

☐  Photo documentation: 4 corners of the room + overhead + utility-stub locations.

# Phase 2 — Electrical scope (T-55 days)

Electrical capacity is the most common cause of install delays. NEC 2023 Articles 422 + 440 govern appliance and refrigeration branch circuits.

☐  Coolers — dedicated 120V/20A circuit per cooler; NEMA 5-20R receptacle within 6 feet.

☐  Hot-food unit (if applicable) — dedicated 120V/20A or 240V/30A per OEM spec.

☐  Kiosk — dedicated 120V/15A circuit on UPS battery backup.

☐  Lighting (overhead + cooler) on facility circuit; not shared with vending loads.

☐  Licensed electrician performs install; permits pulled per local AHJ; load calculation documented.

# Phase 3 — Data scope (T-50 days)

☐  Hardwired ethernet drop at kiosk (preferred over cellular for PCI scope reduction).

☐  If cellular — signal strength ≥ -85 dBm on operator's carrier verified at install location.

☐  Backup connectivity — failover from primary ethernet to cellular within 60 seconds (or vice versa).

☐  Network segmentation — kiosk on a separate VLAN from host corporate network; firewall rules documented.

# Phase 4 — Cold-chain commissioning (T-45 days)

FDA Food Code 2022 §3-501.16 requires TCS foods at ≤ 41°F. Commission each cooler with a 72-hour temperature log before stocking.

☐  Each refrigerated unit run empty for 24 hours; verified to hold ≤ 38°F throughout cycle.

☐  Door-open temperature recovery ≤ 5°F rise; recovery time ≤ 10 minutes.

☐  Temperature-excursion alerting configured: alert at > 41°F sustained > 30 minutes.

☐  Cold-chain alerts route to operator + host facility manager.

# Phase 5 — PCI-DSS scope confirmation (T-40 days)

☐  Operator provides current PCI-DSS v4.0 attestation (SAQ-C-VT or ROC).

☐  Card reader is current-generation EMV + contactless + mobile-wallet capable.

☐  Tokenization confirmed — no PAN data persists on kiosk after transaction.

☐  Encryption confirmed — TLS 1.2+ for all kiosk-to-gateway traffic.

# Phase 6 — ADA + accessibility validation (T-35 days)

☐  Kiosk reach range 15-48 inches per Section 308.

☐  Kiosk touchscreen has audio-output mode or paired mobile app accessibility.

☐  Tactile braille pricing labels where required.

☐  Site walk with host accessibility coordinator; written sign-off.

# Phase 7 — Equipment delivery + placement (T-21 days)

☐  Delivery dock scheduled with host receiving / loading dock.

☐  Pathway clearance verified (doorways ≥ 36 inch wide, ≥ 80 inch tall).

☐  Equipment placed, leveled, and connected to power + data.

☐  Internal lighting + signage installed.

# Phase 8 — Software + planogram configuration (T-14 days)

☐  SKU catalog uploaded to kiosk; pricing + tax rules configured.

☐  Wellness SKUs flagged per host policy (FitPick / NAMA / corporate program).

☐  Allergen labels per FALCPA configured for every SKU.

☐  Loyalty / payroll-deduction integration tested (if applicable).

# Phase 9 — HR badge + employee enrollment (T-10 days)

☐  Host HR provides employee roster with badge IDs for payroll-deduction sync (if applicable).

☐  Privacy notice + opt-in/opt-out flow tested per CCPA/CPRA + state equivalents.

☐  Employee onboarding communications drafted with host comms.

# Phase 10 — Initial stocking + cold-chain validation (T-3 days)

☐  Initial planogram stocked; cold-chain log started at each cooler door.

☐  Refund procedure tested with operator + 2 host volunteers.

☐  Service-ticket creation tested end-to-end.

# Phase 11 — Soft launch (T-0 to T+7)

☐  Communications go out to employees: location, hours, payment methods, refund.

☐  Daily site visit by operator for first 7 days; per-SKU velocity captured.

☐  Stockout incidents logged; planogram tuned daily.

# Phase 12 — 45-day review + planogram refresh

☐  Operator delivers per-SKU velocity report and refund-rate report.

☐  Planogram refresh: drop bottom-quartile SKUs; expand top-quartile facings.

☐  Wellness SKU mix reviewed against host policy target.

☐  Action items + owner + due date documented; QBR cadence confirmed (quarterly).

This checklist is operational guidance; consult licensed electrical + plumbing + permit professionals for code compliance in your jurisdiction.