# Pop-Up Vending for Special Events RFP Template

Deployment timeline, permit checklist, sponsor-integration playbook, and operator scoring framework

Use this RFP template to solicit pop-up vending bids for festivals, conventions, sports activations, and brand experiences. Pop-up programs differ from permanent placements: short deployment, weather exposure, permit complexity, and sponsor-driven SKU mix. This template specifies all four.

# 1. Project overview

Event type + duration: (festival / convention / sports activation / brand experience — specify days on-site, daily attendance, weather risk)

Footprint: Number of pop-up units, footprint per unit (typical 10x10 to 20x20 with machine + queue), power + water needs. Capability framing — describe environment, not anchor event names.

Deployment window: Load-in date, event date(s), load-out date. Typical pop-up timeline T-60 / T-30 / T-7 / T-0 / T+1.

Contract: Single-event or multi-event (e.g., 6-event festival circuit). Operator scopes mobilization cost separately if multi-event.

# 2. Deployment timeline (T-60 to T+1)

| Milestone | Owner | Deliverable |
| --- | --- | --- |
| T-60 days — contract + site survey | Operator + venue ops | Signed contract, site survey with power / water / load-path photos, machine count finalized |
| T-45 days — permit application | Operator | All permits filed per Section 3; copies to venue procurement |
| T-30 days — SKU + sponsor lock | Operator + sponsor lead | SKU catalog locked; sponsor branding art-board approved |
| T-14 days — production + branding | Operator | Vinyl wraps produced; equipment staged; insurance certificates issued |
| T-7 days — pre-event ops review | Operator + venue ops | Walk-through, refund + escalation contact list, restock cadence confirmed |
| T-3 days — staging + delivery | Operator | Machines delivered to staging zone; commissioning + telemetry test |
| T-1 day — load-in + setup | Operator + venue ops | Final placement, power-up, payment-system test, stock to plan |
| T-0 — event day(s) | Operator on-site team | Continuous restock per telemetry; refund handling; uptime ≥ 98% |
| T+1 — load-out + recon | Operator | Equipment removed within agreed window; final reconciliation report within 5 business days |

# 3. Permit + compliance checklist

Pop-up vending typically requires more permits than permanent placements. Operator owns filing; venue provides letters of authorization where required. Reference local health department + fire marshal codes (NFPA 1 / IFC Chapter 38 for temporary structures, local food-service permits).

☐  Temporary food-service permit (health department) — required where TCS food is sold; lead time typically 14-21 days.

☐  Temporary structure / tent permit per NFPA 1 Chapter 25 or IFC Chapter 38 — required for footprints with overhead cover > 200 sq ft.

☐  Electrical permit for temporary power (generator or venue-provided) — local AHJ inspection often required for 100A+ service.

☐  Fire marshal sign-off on egress, extinguisher placement (one 2A:10B:C per 75 ft of travel distance per NFPA 10).

☐  Business license + sales-tax registration for the jurisdiction (where operator is out-of-state).

☐  ABC review if any SKUs include functional botanicals near regulatory line (e.g., kava, CBD).

☐  Certificate of insurance naming venue, event producer, and host municipality as additional insured.

☐  Background-check attestation for all on-site staff (where event requires).

# 4. Sponsor-integration playbook

1. Brand-tier matrix

Operator presents primary / secondary / tertiary logo placement matrix. Primary = full wrap; secondary = side panel + digital sidekick; tertiary = shelf-talker or signage adjacent.

2. Sponsor SKU integration

Operator merchandises sponsor SKUs at eye-level shelves (rows 2-3 of typical machine), with sponsor logo on machine and dedicated digital sidekick callout. Velocity reported separately.

3. Activation extensions

Optional QR / NFC tap at machine pushes to sponsor landing page or sweepstakes entry. Operator provides scan-volume report at T+1 reconciliation.

4. Sponsor compliance

Operator must hold sponsor-brand approval before T-30 lock. Any in-event content change requires sponsor + venue marketing co-approval within 24 hours.

# 5. Outdoor + weather provisions

Equipment rating: NEMA 3R minimum for any equipment exposed to weather; NEMA 4 for hose-down environments. Specify UL 751 listing for vending machines.

Temperature operating range: Most refrigerated vending operates 35°F-100°F ambient. Outdoor deployments below 32°F or above 105°F require shade structures, supplemental cooling, or interior placement.

Weather contingency: Operator commits to weather-event protocol: wind gust > 40 mph or lightning within 8 mi triggers shutdown + lockdown per NWS guidance.

Surge planning: Operator schedules dedicated restock surge crew during peak attendance windows (typically the 2-hour window before and after main event).

# 6. SLA + credits

On-time load-in SLA: 100% of units operational by event open. Each unit late = 5% credit on that line item.

Uptime SLA (event hours): 98%; each percentage point below = 2% credit.

Stockout SLA: Per-SKU stockout > 1 hour during peak window = SKU-line credit for that day.

Refund SLA: On-site refund desk staffed during all event hours; cashless refund auto-credited within 4 hours; cash refund issued on-site.

Reconciliation SLA: Final report within 5 business days of load-out.

# 7. Required attachments (operator response)

☐  Portfolio: 3+ comparable pop-up deployments (capability framing — describe scale and complexity, not anchor event names).

☐  Sample deployment timeline (Section 2) populated for a comparable event.

☐  Permit-filing track record + sample COI.

☐  Sponsor-integration capability deck (Section 4).

☐  Outdoor equipment spec sheets (NEMA / UL ratings).

☐  Sample reconciliation report.

☐  References: 3 event-producer or venue contacts (last 24 months).

# 8. Submission instructions

Format: PDF response via procurement portal.

Due date: (specify — typically 21-30 days from RFP issue, given pop-up timeline pressure)

Mandatory site walk: Operator must attend site walk; capability framing applies — operators are evaluated on capability fit, not prior placements at the named venue.

Award notification: (specify — typically within 14 days after submission close)

Informational template; not legal advice. Permit and insurance requirements vary by jurisdiction — confirm with the local AHJ and risk counsel.